## Slide 1
SECTION 1 · RISK REDUCTION TO DATE
Five-Year Integrity Delivery: Risk Bought Down
$400M integrity capital deployed to date across 50 programs — retiring the system’s highest-consequence assets.
33%
Bare steel main
retired (RBS 7.0)
41%
Cast iron main
retired (RBS 8.2)
~1,080
Field defects closed
across 7 programs
16
Station rebuild programs
underway, $100M to date
% OF PROGRAM DELIVERED — HIGHEST-CONSEQUENCE PROGRAMS
Chart: 
| Cast iron main | Bare steel main | Transmission ILI | Anomaly dig | HCA 24" main | Class-location
% delivered | 41 | 33 | 31 | 29 | 26 | 14
Source: Navigator modeled sample portfolio — synthetic decision-support data, not audited financials. “% delivered” = program budget/schedule completion (proxy for physical retirement); physical miles not carried in the screening record.

## Slide 2
SECTION 2 · CURRENT PLAN YEAR
FY2027 Status: $1.0B Plan Across 100 Programs
$1.00B
Planned capital, FY2027
100
Active programs
$330M
In construction (33%)
$367M
In design (37%)
FY2027 SPEND BY EXECUTION STAGE
Chart: 
| Construction (27) | Procurement (20) | Design (37) | Planning (16)
FY2027 $M | 330.3 | 176.9 | 367.3 | 125.5
Bars labelled with program count in parentheses.
SCOPE PLANNED — FY2027 (5-YEAR PLAN)
Meters
~43,600
201,720 / 5yr
Services
~40,300
188,440 / 5yr
Main & capacity miles
~215
1,044 / 5yr
Stations
~25
136 / 5yr
Source: Navigator modeled sample portfolio — synthetic decision-support data, not audited financials. FY2027 physical scope is a modeled slice of the 2027–2031 plan (pro-rated by spend); per-year physical splits not in record.

## Slide 3
SECTION 3 · FIVE-YEAR CAPITAL PLAN
$5.0B Five-Year Capital by Asset Class
Integrity & operations $2.50B · New business & capacity $2.50B
Chart: 
| New business | Capacity reinforcement | Transmission | Distribution | Compressor stations | Regulator stations | Defect remediation | Well operations
5yr $M | 1502.9 | 997 | 780.3 | 610.2 | 374.1 | 314.5 | 226.6 | 194.2
Source: Navigator modeled sample portfolio — synthetic decision-support data, not audited financials.

## Slide 4
SECTION 4 · BUDGET OPTIONALITY
$100M Two-Year Reduction: Where It Comes From
$100M
Target reduction — FY2027 + FY2028
$113.8M
Modeled availability (target met, +$13.8M headroom)
$0
Integrity / regulatory-committed dollars cut
MODELED SAVINGS vs $50M ANNUAL TARGET
Chart: 
| FY2027 | FY2028
Modeled available | 52.7 | 61.1
$50M target | 50 | 50
WHAT MOVES vs WHAT'S PROTECTED
Touchable — growth work
5 new-business programs, risk-benefit 0.8–1.2, class A/B. Deferrable connections & growth mains.
Protected — do not cut
61 programs locked by regulatory commitment or construction lock-in — all integrity and duty-to-serve work, including bare steel & cast iron.
Source: Navigator modeled sample portfolio — synthetic decision-support data, not audited financials. Combined from two build_budget_scenario runs ($50M FY2027 + $50M FY2028); modeled heuristic, validate commitments before action.

## Slide 5
APPENDIX A · OPTIONALITY DETAIL
Projects Making Up the $100M Optionality
Program (ID) | Class | RBS | FY2027 | FY2028 | 2-Yr Total
Metro Residential New Services (NB-2021) | A | 0.8 | $14.41M | $12.26M | $26.67M
Metro Residential New Meter Installations (NB-2001) | A | 0.8 | $14.51M | $11.84M | $26.35M
Master-Planned Community New Services (NB-2027) | A | 0.8 | $11.91M | $11.06M | $22.98M
Master-Planned Community Meter Program (NB-2007) | A | 0.8 | $11.91M | $11.06M | $22.98M
Metro Growth-Corridor New Distribution Mains (NB-2011) | B | 1.2 | — | $14.87M | $14.87M
Total — 5 growth programs |  |  | $52.75M | $61.09M | $113.84M
All five are new-business growth programs (risk-benefit 0.8–1.2). The two-year total exceeds the $100M target by $13.8M, giving the board margin to stop short or phase the reduction.
Source: Navigator modeled sample portfolio — synthetic decision-support data, not audited financials.

## Slide 6
APPENDIX B · PROTECTED
Protected Programs — Excluded From Any Cut
Program (ID) | RBS | Regulatory authority | Due date
Cast Iron Main Replacement (GAS-1022) | 8.2 | Commission cast iron retirement plan | Dec 31, 2031
HCA 24-Inch Transmission Main Replacement (GAS-1007) | 7.8 | PHMSA corrective action order | Jun 30, 2030
Leak-Prone Bare Steel Main Replacement (GAS-1021) | 7.0 | Commission leak-prone pipe plan | Dec 31, 2031
Priority Anomaly Dig Program (GAS-1010) | 6.5 | Integrity mgmt remediation schedule | Aug 31, 2031
Transmission In-Line Inspection Program (GAS-1009) | 6.0 | 49 CFR 192 Subpart O assessment | Dec 31, 2031
Class Location Change Pipeline Replacement (GAS-1014) | 5.6 | Class-location remediation plan | Mar 31, 2031
MAOP Reconfirmation Hydrotest (GAS-1011) | 4.2 | 49 CFR 192.624 MAOP plan | Jul 1, 2030
Emergency Shutdown Valve Testing (GAS-1038) | 3.7 | State pipeline safety inspection | Oct 31, 2029
Casing Vent Remediation Program (GAS-1002) | 3.5 | State underground storage order | Oct 31, 2029
Transmission Coating Rehabilitation (GAS-1016) | 3.1 | Pipeline safety corrosion response | May 31, 2030
Top 10 of 61 protected programs, ranked by risk-benefit score. These carry the system’s highest consequence and are locked by regulatory commitment — cutting them is off the table.
Source: Navigator modeled sample portfolio — synthetic decision-support data, not audited financials.